## Slide 1: Software Engineering
Tenth Edition
Chapter 23
Project planning
Copyright © 2016, 2011, 2006 Pearson Education, Inc. All Rights Reserved
Notes: If this PowerPoint presentation contains mathematical equations, you may need to check that your computer has the following installed:
1) MathType Plugin
2) Math Player (free versions available)
3) NVDA Reader (free versions available)

## Slide 2: Learning Objectives
Project Planning
Project scheduling
Agile planning

## Slide 3: Project Scheduling

## Slide 4: Project Scheduling (What)
Project scheduling is the process of deciding how the work in a project will be organized as ______________, and when and how these tasks will be executed.
Estimate for each task
  Calendar time needed to complete each task,
  the effort required and
  who will work on the tasks that have been identified.
  Resources needed to complete each task
separate tasks

## Slide 5: Project Scheduling Activities(How)
Split project into tasks and
Estimate time and resources required to complete each task.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Organize tasks concurrently to make optimal use of workforce.

## Slide 6: The Project Scheduling Process

## Slide 7: Scheduling Problems
Difficulty/Cost: Estimating the difficulty of problems and hence the cost of developing a solution is hard.
Productivity: Productivity is not proportional to the number of people working on a task.
Communication overheads: Adding people to a late project makes it later because of communication overheads.
Contingency: The unexpected always happens. Always allow contingency in planning.

## Slide 8: Schedule Presentation
Graphical notations are normally used to illustrate the project schedule.
Task period: These show the project breakdown into tasks. Tasks should not be too small. They should take about a week or two.

## Slide 9: Schedule Presentation
Calendar-based
  Bar charts are the most commonly used. They show the schedule as activities or resources against time.
Activity networks
  Show task dependencies

## Slide 10: Project Tasks
Project tasks are the basic planning element. Each has:
  A duration : in calendar days or months,
  An effort estimate, which shows the number of person-days or person-months to complete the work,
  A deadline: by which the activity should be complete,
  A defined end-point, which might be a document, the holding of a review meeting, the successful execution of all tests, etc.

## Slide 11: Milestones and Deliverables
Milestones are points in the schedule against which you can assess progress
Deliverables are work products that are delivered to the customer

## Slide 12: Tasks, Durations, and Dependencies
Task | Effort (person-days) | Duration (days) | Dependencies
T1 | 15 | 10 | blank
T2 | 8 | 15 | blank
T3 | 20 | 15 | T1 (M1)
T4 | 5 | 10 | blank
T5 | 5 | 10 | T2, T4 (M3)
T6 | 10 | 5 | T1, T2 (M4)
T7 | 25 | 20 | T1 (M1)
T8 | 75 | 25 | T4 (M2)
T9 | 10 | 15 | T3, T6 (M5)
T10 | 20 | 15 | T7, T8 (M6)
T11 | 10 | 10 | T9 (M7)
T12 | 20 | 10 | T10, T11 (M8)

## Slide 13: Activity Bar Chart

## Slide 14: Staff Allocation Chart

## Slide 15: Agile Planning

## Slide 16: Agile Planning
The customer’s priorities and requirements change so it makes sense to have a flexible plan that can accommodate these changes.

## Slide 17: Agile Planning Stages
Stage1: Release planning
  looks ahead for several months
  decides on the features that should be included

## Slide 18: Agile Planning Stages
Stage2: Iteration planning
  it has a shorter term outlook, and focuses on planning the next increment of a system.
  typically 2-4 weeks of work for the team.

## Slide 19
  Stage 1:
  Establish the general objectives
  Design the software architecture.
  Backlog
  Stage 2:
  A series of sprint cycles, where each cycle develops an increment of the system.
  Stage 3:
  Closure phase wraps up the project
Approaches to Agile Planning

## Slide 20: Story-based Agile Planning
1. Stories: based on user stories that reflect the features that should be included in the system.
2. Rank: rank them in order of the amount of time they think it will take to implement the story.

## Slide 21: Story-based Planning Cont.
3. Effort points: Stories are assigned ‘effort points’ reflecting their size and difficulty of implementation
4. Measure: The number of effort points implemented per day is measured giving an estimate of the team’s ‘velocity’

## Slide 22: The Planning Game
Iteration planning:
  Stories: Stories to be implemented in each iteration are chosen
  Number: With the number of stories reflecting the time to deliver an iteration (usually 2 or 3 weeks).
Release planning involves:
  Stories: selecting and refining the stories that will reflect the features to be implemented in a release
  Order: the order in which the stories should be implemented.

## Slide 23: The Planning Game Cont.
The developers break down stories into development tasks.
  A development task should take 4-16 hours.
  All of the tasks that must be completed to implement all of the stories in that iteration are listed.
  The individual developers then sign up for the specific tasks that they will implement.
Benefits:
  The whole team gets an overview of the tasks to be completed in an iteration.

## Slide 24: Benefit: Software Delivery
A software increment is always delivered at the end of each project iteration.
If the features to be included in the increment cannot be completed in the time allowed, the scope of the work is reduced.
The delivery schedule is never extended.

## Slide 25: Agile Planning Difficulties
Agile planning is reliant on customer involvement and availability
  This can be difficult to arrange, as customer representatives sometimes have to prioritize other work and are not available for the planning game.
  Furthermore, some customers may be more familiar with traditional project plans and may find it difficult to engage in an agile planning process.

## Slide 26: Software you may use for management
https://trello.com/
https://taiga.io/

## Slide 27: News
Agile management: Scrum, Kanban or both?